## Workplan
Task_ID | Workstream | Task | Owner | Due_Date | Status | Notes
T-0001 | Project Management | Confirm scope & success criteria | Asha | 2026-02-03 | In progress | Initial draft shared; needs partner sign-off
T-0002 | Customer | Draft customer interview guide | Ravi | 2026-02-05 | Not started
T-0003 | Financial Model | Build baseline revenue model | Mina | 2026-02-06 | Not started | Awaiting updated assumptions
T-0004 | Data | Request data extract from Finance | TBD | 2026-02-02 | Blocked | Waiting for Finance confirmation
T-0005 | SteerCo | Draft steerco storyline (v1) | Leo | 2026-02-04 | Not started
T-0006 | Market | Compile competitor benchmark table | Nina | 2026-02-06 | In progress | Using last year's deck as a starting point
T-0007 | Ops | Map current-state process (high level) | Omar | 2026-02-07 | Not started
T-0008 | Project Management | Schedule client working session | Asha | 2026-02-02 | Not started | Need to align on attendees
T-0009 | SteerCo | Create 1-slide executive summary | Leo | 2026-02-04 | Not started | Will depend on scope decision
T-0010 | Data | Confirm definition of 'active customer' metric | Ravi | 2026-02-03 | In progress | Clarify with client analytics lead